## Your Marketing Plan
New Ownership Marketing Plan
Where you see this colour please input information
Task |  | Comments | Approx. cost (excl. GST) | Qty | Budget (excl. GST) | Target | Actions | 16 Weeks prior to relaunch | 12 Weeks prior to relaunch | 8 Weeks prior to relaunch | 4 Weeks Prior to relaunch | Opening Week
Collateral Development
| Decide on - Develop New Logo | This should be developed 20 - 24 weeks out from practice opening. Use colours that compliment your practice fit out. Develop brief for logo using practice fit out as a base. Logo design takes approximately 8 to 12 hours. Graphic design fee as follows: - $75+gst per hour for comprehensive members - $85+gst per hour for essential members | 750 | 1 | 750 | Potential customers from local area | Engage & create a brief for graphic designer
| Stationery - Business cards - Letterhead - With compliments slips ProMarket Options - Warranty cards - Glasses care cards | Stationery design (letterheads, business cards and with compliments slip) takes approximately 3 to 6 hours. Graphic design fee as follows: - $75+gst per hour for comprehensive members - $85+gst per hour for essential members Warranty and glasses care can be orderd through ProMarket. We can create a custom version for the specified design fees above. | 375 | 1 | 375 | Customers | Engage & create a brief for graphic designer
| Photography | Research local photographers and book in a time that all staff and previous practice owner and current can attend. | 1600 | 1 | 1600 | Customers | Engage local photographer
| Develop Shopfront and Internal Signage |  | 2000 | 1 | 2000 | Customers | Engage & create a brief for graphic designer
Communicating with Patients
| Re-Launch Postcard Once wording and message has been developed for this postcard. It can become the basis for all launch marketing wording. | Use postcard to communicate the improvements you have made to the practice facilities, equipment and products. Articulate why people should choose your practice. Communicate old owner staying on and endorses new owners eye care philosophies and clinical skills. | 2 | 500 | 1000 | Targeted patients (Gen X women) who have attended the practice in the past six years | Engage & create a brief for graphic designer
| Re-Launch SMS | Use SMS to communicate to all patients on your database new ownership and you have same values as old ownership. | 0.19 | 5000 | 950 | All patients who have attended the practice in the past six years | Use ProMarket
| Re-Launch Emailer | Use Email to communicate to all patients on your database new ownership and you have same values as old ownership. | 0 | 10000 | 0 | All patients who have attended the practice in the past | Use ProMarket
| Launch event | Create launch event. Invite staff that work in local area, local health professionals and VIPS from your local area and your database. |  |  | 1000 | Health professionals/local store owners. VIPS from local area and on database | Engage a supplier & create a brief for graphic designer
| Execute ProVision National Marketing Campaign | Register for ProVision campaign. Only run this campaign if it compliments the launch marketing. |  |  | [Insert Quote] | Customers attending the centre or shopping strip | Register for the campaign
Attracting New Patients
| Interchangeable practice A-Frame with rotational messages | Enquire with local council if any sign restrictions | 350 | 0 | 0 | Customers attending the centre or shopping strip
| Invest in eye-catching window displays (consider window dresser) | This can either be a staff member or a local window dresser. Budget $250 per window change over | 250 | 0 | 0 | Customers attending the centre or shopping strip
| Develop relationships with GPs and specialists in local area. Develop - letter of introduction and introduce your new owner | Distribute hard copy to local health professionals including chemists |  |  | 200 | Health professionals | Refer Us materials in GP section of optom.provision.com.au
| Develop cross promotional offers with local businesses where appropriate | Custom Quote for Materials |  |  | 200 | customers attending the centre or shop strip
| Local Sponsorship | Sporting club, schools, contact and offer goods and services for promotion. |  |  | 1000 | Potential customers from local area
| Local newspaper advertising and editorials | Design approx. $150 + Newspaper placement cost |  |  | 2000 | If no quality outlet exists disregard | sourcing quote from local provider
| Local Radio advertising | Regional practice opportunity |  |  | [Insert Annual Budget] | If no quality outlet exists disregard | sourcing quote from local provider
| Local TV advertising (regional) | Regional practice opportunity |  |  | [Insert Annual Budget] | If no quality outlet exists disregard | sourcing quote from local provider
Create Digital Presence
| Create an independent practice website that complements your new practice fit out | Your dedicated practice website should be an extension of your practice's positioning and offerings (use your Why Choose Use points to promote your points of difference or speak to us if you need help to develop). Your website design should be brand-aligned to help patients easily recognise your practice. We work with two preferred suppliers to provide a range of website developments styles and options to suit your individual needs and budget. Website prices are as follows: - Basic (kapsule) website - approx. $2,500+GST - Custom website - approx. $6,000+GST - Advanced website - approx. $8,000+GST | 2500 |  | 2500 | Potential customers who live or work in your local area
| Set-up in search engine optimisation for your website (SEO) | SEO helps to increase your Google rankings and online visibility so that you can be easily found by customers who are searching for your services. It helps you to stay ahead of your competitors. SEO requires a monthly investment which starts from $400+GST per month. While it is recommended that you invest in SEO from the time you develop your website, you can choose to invest in it a few months down the track. | 400 | 12 | 4800
| Update practice pages on the ProVision consumer website on a monthly basis | Privilege of Membership | 0 |  | 0 | Potential customers who live or work in your local area | Dedicate a team member to manage
| Set-up and update Google+ and Google My Business listing | Free Google Service | 0 |  | 0 | Potential customers who live or work in your local area | Dedicate a team member to manage
| Create Digital google search ads, refer to ProVision for Google advertising instructions. | Spend $300 per month to promote new domain name. Execute for 6 months until site established | 300 | 6 | 1800 | Potential customers who live or work in your local area | Create search ads required to promote practice
| Set-up Facebook account and update 2-3 times per week | Factor in the time management of Facebook into the staff or practice manager job description. Make the new practice creation the main story running through the posts | 200 | 12 | 2400 | Potential customers who live or work in your local area | Dedicate a team member for content production
| Facebook Advertising (refer to ProVision's member site to learn about Facebook Advertising) | Suggest $5 per day over monthly period. $200 a month Once page established | 200 | 12 | 2400 | Potential customers who live or work in your local area | Dedicate a team member for content production
| TOTAL |  |  |  | 24975