## Instructions
Launch Checklist Instructions for Use
This spread sheet is designed to allow you to view all the tasks that you need to complete in each category . It will then sort those tasks into a priority action based on when you would like to complete each ask. Some tasks you will want to complete before opening your practice like hiring staff, installing your software and buying your stock . Whereas some other items you might choose to defer until after your opening date
INSTRUCTIONS
1. Select the New Launch Menu Tab
2. Enter your desired date for completion of each task in the red cells
The spreadsheet will then caluculate when you should commence each task based on the lead time that in indicated in column E
3. Select Launch Checklist Tab
Go to cell 1D Target Start Date for Task
Click on the sorting arrow and select 'Sort Oldest to Newest'
The spreadsheet will then sort the tasks into a Priority Action Plan for you

## New Launch Menu
| Task | Comments | Approx. cost if known | Lead time to completion in weeks | Completion Target Date | Target Start Date for Task | Owner of Task | Links to Assist | Progress Comments | Complete
Business Plan to Reality
1 | Create your business plan | Reach out to your Business Coach for template and guidance |  | 18.2 | 2020-12-25 | 2020-08-19 14:24
2 | Secure an Accountant | Refer to the 'Tips on organising your structure and support' document |  | 18 | 2020-12-25 | 2020-08-21
3 | Secure a Solicitor | Refer to the 'Tips on organising your structure and support' document |  | 18 | 2020-12-25 | 2020-08-21
4 | Secure a Financial Advisor | Refer to the 'Tips on organising your structure and support' document |  | 18 | 2020-12-25 | 2020-08-21
5 | Decide on your company structure | Refer to ‘Tips on Establishing Your Structure’ |  | 18 | 2020-12-25 | 2020-08-21
6 | Register Company name | Refer to the 'Get legally set up for business' document |  | 16.2 | 2020-12-25 | 2020-09-02 14:24
7 | Register ABN, TFN and GST | Refer to the 'Get legally set up for business' document |  | 16.2 | 2020-12-25 | 2020-09-02 14:24
8 | Secure Insurances: • Professional Indemnity insurance • Public Liability | OAA Ph: (03) 96636833 Membership of Optometrists Association Australia includes Professional Indemnity Insurance. |  | 16 | 2020-12-25 | 2020-09-04
9 | Investigate additional insurances you require: • Building/stock • Income protection • Loan protection • Life | Membership of Optometrists Association Australia includes Professional Indemnity Insurance. |  | 16 | 2020-12-25 | 2020-09-04
10 | Schedule and diarise fortnightly catch ups with Business Coach (for ProVision Comprehensive Members) | Contact your Business Coach |  | 16 | 2020-12-25 | 2020-09-04
11 | Register for ProVision leasing assistance | Contact Business Services |  | 17.5 | 2020-12-25 | 2020-08-24 12:00
12 | Secure bank & set up business bank account | Refer to the ‘Discover Finance Options For You’ document |  | 18 | 2020-12-25 | 2020-08-21
13 | Organise finance if required | Refer to the ‘Discover Finance Options For You’ document |  | 18 | 2020-12-25 | 2020-08-21
14 | Download the ‘Get Legally Set Up for Business’ checklist and ensure all items are actioned or scheduled for action | Refer to the 'Get legally set up for business' document |  | 12 | 2020-12-25 | 2020-10-02
Location, Location, Location
15 | Discuss lease and fit out questions with Business Services at ProVision | Reach out to Mark Corduff |  | 18 | 2020-12-25 | 2020-08-21
16 | Refer to your Business Plan financial forecasts to establish the level of rent you can comfortably afford |  |  | 16 | 2020-12-25 | 2020-09-04
17 | Familiarise yourself with some of the leasing principles in the document provided | Download the '5 tips to consider' document for leasing guidance |  | 14 | 2020-12-25 | 2020-09-18
18 | Prior to signing lease, have Mark Corduff and your solicitor review it | Contact Business Services |  | 12 | 2020-12-25 | 2020-10-02
19 | Contact ProVision preferred referral partners to discuss your plans and arrange quotes for your fitout if this is required | Refer to the 'More about your fitout' link and contact Business Services to discuss options |  | 16 | 2020-12-25 | 2020-09-04
20 | Download the WOW fitout examples and tips for your practice for inspiration and understanding | Refer to the 'More about your fitout' link |  | 16 | 2020-12-25 | 2020-09-04
21 | Organise Utilities (Gas, Electricity, Internet) |  |  | 8 | 2020-12-25 | 2020-10-30
22 | Rent payments & bond (or bank guarantee) to be organised with landlord | Contact your landlord |  | 4 | 2020-12-25 | 2020-11-27
Money Matters
23 | Purchase an accounting software system |  |  | 8 | 2020-12-25 | 2020-10-30
24 | Access ProLearnMAX - Financial Foundations | Complete all modules to increase your financial knowledge |  | 8 | 2020-12-25 | 2020-10-30 |  | https://prolearnmax.provision.com.au/admin/login-next.php
25 | Set your financial goals for the next 12 months | Where is the business now? Where is the business heading? How is the business going to get there? Set long term strategic goals |  | 16.4 | 2020-12-25 | 2020-09-01 04:48
26 | Calculate your costs | Make a list of expenses - Refer your Business Coach E.g. Wages, Rent, Utilities, Fees, Marketing, Accounting etc. |  | 16.4 | 2020-12-25 | 2020-09-01 04:48
27 | Predict your sales income | Consultation Income Retail Income Sundry Income |  | 16.4 | 2020-12-25 | 2020-09-01 04:48
28 | Complete the P&L/Cashflow Template | Contact your Business Coach for guidance |  | 16.4 | 2020-12-25 | 2020-09-01 04:48 |  | https://optom.provision.com.au/wp-content/uploads/sites/3/2020/08/Practice-Budget-Template-GF-April-2020-1.xls
29 | Review and refine your financial forecasts and assumptions | Review all data on P&L and Cash Flow statement to ensure accuracy and achievable - Refer your Business Coach for guidance |  | 5 | 2020-12-25 | 2020-11-20
30 | Enter data into accounting software to create full year budget P&L | Your Accountant or Bookkeeper will be able to complete this task |  | 5 | 2020-12-25 | 2020-11-20
Your Dream Team
31 | Create Position Descriptions for all positions | Can be found in recruitment framework |  | 9 | 2020-12-25 | 2020-10-23
32 | Review Master Task List for the Practice to ensure all duties for your practice are included and also are allocated to team members |  |  | 9 | 2020-12-25 | 2020-10-23
33 | Review the Recruitment Framework to gain a richer understanding of the recruiting process and how PV can support you |  |  | 9 | 2020-12-25 | 2020-10-23
34 | Contact People and Culture Team to commence recruiting process |  |  | 8 | 2020-12-25 | 2020-10-30
35 | Ensure all contracts for team members are finalised | This time frame will vary depending on the notice period of the applicant |  | 4 | 2020-12-25 | 2020-11-27
36 | All new team members to complete Induction module on ProLearn Max plus complete and bespoke additional in practice induction |  |  | 2 | 2020-12-25 | 2020-12-11
37 | Diarise new employee formal feedback sessions for end of week 1 | End of week 1 |  | -1 | 2020-12-25 | 2021-01-01
38 | Diarise new employee feedback sessions for end of week 2 | End of week 2 |  | -2 | 2020-12-25 | 2021-01-08
39 | Diarise new employee formal feedback sessions foe end of month 1 | End of month 1 |  | -4 | 2020-12-25 | 2021-01-22
40 | Diarise new employee formal feedback sessions for end of month 2 | End of month 2 |  | -8 | 2020-12-25 | 2021-02-19
41 | Diarise new employee formal feedback sessions for end of month 3 | End of month 3 |  | -13 | 2020-12-25 | 2021-03-26
42 | Diarise new employee formal feedback sessions pror to the completeion of probation period | Prior to completion of probation period |  | -13 | 2020-12-25 | 2021-03-26
43 | Set Team Meeting dates for 12 months and publish to team |  |  | 1 | 2020-12-25 | 2020-12-18
44 | Diarise Performance Management Discussions for each team member |  |  | 1 | 2020-12-25 | 2020-12-18
45 | Block off weekly time to observe each team members behaviour and performance | Allowing time every week for this will be one of you greatest investments in the positive culture and performance of your team |  | 1 | 2020-12-25 | 2020-12-18
46 | Create a Team Recognition Plan |  |  | 1 | 2020-12-25 | 2020-12-18
47 | Start your professional development as a business owner by making an appointment with your Business Coach to create your development plan | The plan might include reading The Carrot Principle, Dare to Lead and Fixing Communication |  | 4 | 2020-12-25 | 2020-11-27
Your Irresistable Offer
48 | Why Choose You? Develop your "Why choose us" key points of difference | Clarify your 'brand' position & point of difference |  | 12 | 2020-12-25 | 2020-10-02
49 | Identify yourTarget Market | Council Census Analysis & Surrounding Suburbs |  | 12 | 2020-12-25 | 2020-10-02
50 | Clarify your patient 'Type' | High End, Middle Market, Value Patient |  | 12 | 2020-12-25 | 2020-10-02
51 | Decide on your budget spend for inventory | How much has been put aside in your original business plan to purcahse frame stock and does this need to be revised? |  | 12 | 2020-12-25 | 2020-10-02
52 | Look at & decide on display capacity (How many units will be on display & what additional stock you will hold on hand [1-2 units]) | What unit numbers do you need for an impactful visual display ? |  | 12 | 2020-12-25 | 2020-10-02
53 | Decide on gender split & display capacity by gender & demographic | What is the percentage of stock mix by Womens, Mens (and kids if applicable)? This will come from your census report , a historical range review or the previous practice sell thru if available |  | 12 | 2020-12-25 | 2020-10-02
54 | Working with your BC , identify best suppliers for your target market | Reference: Preferred Supplier handbook & Top 50 Brands by Price point |  | 10 | 2020-12-25 | 2020-10-16
55 | Organise time to meet with frame suppliers | Ensure to be clear on units by display, gender split, OTB & under stock to be held (1-2 units) when meeting with reps |  | 8 | 2020-12-25 | 2020-10-30
56 | Negotiate terms with supplier prior to signing off purchase | Is this consignment? Are there extended terms? What is the agreed rotation policy and the exit strategy by brand? Do you have an opening order /new memebr offers ? |  | 8 | 2020-12-25 | 2020-10-30
57 | Clarify delivery dates for frame orders prior to practice opening | What is the turnaround time from order to deliver and will this be in time for set up & launch? |  | 8 | 2020-12-25 | 2020-10-30
58 | Implement pricing strategy | Work with you BC to create a pricing strategy that delivers strong margin and clear price points. |  | 6 | 2020-12-25 | 2020-11-13
59 | Arrange brand training on frames and technical training for lenses | Dependent on recruitment stage it will be of benefit to have a training night with a couple of lead suppliers on the features and benefits of the brands and lenses sold in practice |  | 4 | 2020-12-25 | 2020-11-27
60 | Delivery & indentation of frame stock into system | This date should have been agreed during closing negotiations with frame suppliers |  | 4 | 2020-12-25 | 2020-11-27
61 | Inline with delivery, enter SOH into the system | Ensure to clasify as specifically as possible (style, pp, gender, SKU) as this will make reporting easier later on when analysing sell-thru. Confirm correct delivery and raise any discrepancies with supplier now |  | 4 | 2020-12-25 | 2020-11-27
62 | Finalise Visual Merchandising Plan-O-Gram | Work with BC |  | 3 | 2020-12-25 | 2020-12-04
63 | ProSupply and Supply & Fit training | Team & owner training with BC or online training modules |  | 2 | 2020-12-25 | 2020-12-11
64 | Plan to complete a physical stocktake on or around settlement day |  |  | 1 | 2020-12-25 | 2020-12-18
65 | Develop a simple lens pricing matrix document to assist the team to explain to customers the features ana benefits of the lenses in each price category | Ask your Business Coach for examples |  | 1 | 2020-12-25 | 2020-12-18
66 | Decide which price tags you will use | Source price tag/ barcoding system |  | 4 | 2020-12-25 | 2020-11-27
67 | Check with Practice Management System (PMS )provider which barcode scanner is compatable with your PMS soft ware >> Purchase barcode scanner | This will increase accurancy and speed for all stock entry , POS transactions and stocktakes |  | 4 | 2020-12-25 | 2020-11-27
68 | Arrange PMS system training for the Team |  |  | 1 | 2020-12-25 | 2020-12-18
69 | If transferring from paper patient record cards to digital patient records decide the process . | Refer to your Business Coach for suggestions |  |  | 2020-12-25 | 2020-12-25
70 | Merchandise frames into display | Work to Plan-o-Gram |  | 1 | 2020-12-25 | 2020-12-18
360 Degrees of Communication
71 | Develop new logo | Engage & create a brief for graphic designer | 500 | 16.1 | 2020-12-25 | 2020-09-03 07:12
72 | Develop shopfront, windows and internal signage | Engage & create a brief for graphic designer | 2000 | 16 | 2020-12-25 | 2020-09-04
73 | Commence process of creating your independent practice website | Make an apppoinment with PV Marketing Team to discuss options |  | 16.1 | 2020-12-25 | 2020-09-03 07:12
74 | Set-up Google My Business listing | Dedicate a team member to manage |  | 16 | 2020-12-25 | 2020-09-04
75 | Set-up Facebook account and update 2-3 times per week | Dedicate a team member for content production | 200 | 16 | 2020-12-25 | 2020-09-04
76 | Develop your stationery - Business cards - Letterhead - Warranty cards - Glasses care cards | Engage & create a brief for graphic designer | 500 | 12 | 2020-12-25 | 2020-10-02
77 | Develop marketing communication plan to patients including : relaunch postcards ,SMS and emails | Engage & create a brief for graphic designer | 2 | 12 | 2020-12-25 | 2020-10-02
78 | Create google search ads, refer to ProVision for Google advertising instructions. | Create search ads required to promote practice | 300 | 12 | 2020-12-25 | 2020-10-02
79 | Arrange Practice photography | Engage local photographer | 1600 | 8 | 2020-12-25 | 2020-10-30
80 | Create Launch Event. Invite staff that work in local area, local health professionals and VIPS from your local area and your database | Engage a supplier & create a brief for graphic designer |  | 8 | 2020-12-25 | 2020-10-30
81 | Create interchangeable practice A-Frame with rotational messages |  | 350 | 8 | 2020-12-25 | 2020-10-30
82 | Develop relationships with GPs and specialists in local area. Develop - letter of introduction and introduce your new owner | Refer Us materials in GP section of optom.provision.com.au |  | 4 | 2020-12-25 | 2020-11-27
83 | Develop cross promotional offers with local businesses where appropriate |  |  | 4 | 2020-12-25 | 2020-11-27
84 | Research local sponsorship opportunities |  |  | 8 | 2020-12-25 | 2020-10-30
85 | Local newspaper advertising and editorials if relevant | sourcing quote from local provider |  | 8 | 2020-12-25 | 2020-10-30
86 | Local Radio advertising if relevant | sourcing quote from local provider |  | 8 | 2020-12-25 | 2020-10-30
87 | Local TV advertising (regional) if relevant | sourcing quote from local provider |  | 8 | 2020-12-25 | 2020-10-30
88 | Update practice pages on the ProVision consumer website on a monthly basis | Dedicate a team member to manage |  | 8 | 2020-12-25 | 2020-10-30
89 | Create a Facebook Advertising plan (refer to ProVision's member site to learn about Facebook Advertising) | Dedicate a team member for content production | 200 | 8 | 2020-12-25 | 2020-10-30
90 | Invest in eye-catching window displays (consider window dresser) |  | 250 | 4 | 2020-12-25 | 2020-11-27
91 | Register for any relevant ProVision marketing campaigns. | Register for the campaign |  | 1 | 2020-12-25 | 2020-12-18
92 | Liase with My Health First to ensure their software is embedded into your website |  |  | 4 | 2020-12-25 | 2020-11-27
93 | Complete application for My Health First ( online booking) |  |  | 4 | 2020-12-25 | 2020-11-27
Keeping it Consistent and Legal
94 | Obtain your Log in details from Australian Retialers Association (ARA) | Call ARA on 1300 368 041 Take option 1 (one).Quote your PV Member number and they will give new login details. Alternatively contact Kylie Parry, People and Culture Advisor on (03) 8544 3906 or email: kparry@provision.com.au |  | 8 | 2020-12-25 | 2020-10-30
95 | Login to ARA site and familiarise yourself with Employee Agreement templates , policy documents and the Award conditions |  |  | 8 | 2020-12-25 | 2020-10-30 |  | https://www.enablehr.com.au/ara/
96 | Access ARA Instructions on "How To Create a policy | insert link to ARA "How to Create a Policy Document" (new Document) |  | 8 | 2020-12-25 | 2020-10-30
97 | Produce all policies relevant to your practice through ARA portal | Select each policy relevant to your practice , complete details required in the templates. Make one copy availble to the team to read and file on copy in your policy and procedure file for future reference |  | 8 | 2020-12-25 | 2020-10-30
98 | Review AWARD conditions and salary ranges for each position on ARA website |  |  | 8 | 2020-12-25 | 2020-10-30
99 | Create Employee Agreements ( Contracts) through enable HR (ARA) |  |  | 4 | 2020-12-25 | 2020-11-27
100 | Enter each team members details onto your EnableHR portal for easy management of empolyee details,perfomance management etc |  |  | 4 | 2020-12-25 | 2020-11-27
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
Formulas:
Target Start Date for Task = IFERROR(IF([Completion Target Date]-7*[Lead time to completion in weeks]<=0,"",[Completion Target Date]-7*[Lead time to completion in weeks]),"")

## Launch Checklist
Column1 | Task | Comments | Target Start date for task | Owner of Task | Links to Assist | Progress Comments | Complete
1 | Create your business plan | Reach out to your Business Coach for template and guidance | 2020-08-19 14:24
2 | Secure an Accountant | Refer to the 'Tips on organising your structure and support' document | 2020-08-21
3 | Secure a Solicitor | Refer to the 'Tips on organising your structure and support' document | 2020-08-21
4 | Secure a Financial Advisor | Refer to the 'Tips on organising your structure and support' document | 2020-08-21
5 | Decide on your company structure | Refer to ‘Tips on Establishing Your Structure’ | 2020-08-21
12 | Secure bank & set up business bank account | Refer to the ‘Discover Finance Options For You’ document | 2020-08-21
13 | Organise finance if required | Refer to the ‘Discover Finance Options For You’ document | 2020-08-21
15 | Discuss lease and fit out questions with Business Services at ProVision | Reach out to Mark Corduff | 2020-08-21
11 | Register for ProVision leasing assistance | Contact Business Services | 2020-08-24 12:00
25 | Set your financial goals for the next 12 months | Where is the business now? Where is the business heading? How is the business going to get there? Set long term strategic goals | 2020-09-01 04:48
26 | Calculate your costs | Make a list of expenses - Refer your Business Coach E.g. Wages, Rent, Utilities, Fees, Marketing, Accounting etc. | 2020-09-01 04:48
27 | Predict your sales income | Consultation Income Retail Income Sundry Income | 2020-09-01 04:48
28 | Complete the P&L/Cashflow Template | Contact your Business Coach for guidance | 2020-09-01 04:48 |  | https://optom.provision.com.au/wp-content/uploads/sites/3/2020/08/Practice-Budget-Template-GF-April-2020-1.xls
6 | Register Company name | Refer to the 'Get legally set up for business' document | 2020-09-02 14:24
7 | Register ABN, TFN and GST | Refer to the 'Get legally set up for business' document | 2020-09-02 14:24
71 | Develop new logo | Engage & create a brief for graphic designer | 2020-09-03 07:12
73 | Commence process of creating your independent practice website | Make an apppoinment with PV Marketing Team to discuss options | 2020-09-03 07:12
8 | Secure Insurances: • Professional Indemnity insurance • Public Liability | OAA Ph: (03) 96636833 Membership of Optometrists Association Australia includes Professional Indemnity Insurance. | 2020-09-04
9 | Investigate additional insurances you require: • Building/stock • Income protection • Loan protection • Life | Membership of Optometrists Association Australia includes Professional Indemnity Insurance. | 2020-09-04
10 | Schedule and diarise fortnightly catch ups with Business Coach (for ProVision Comprehensive Members) | Contact your Business Coach | 2020-09-04
16 | Refer to your Business Plan financial forecasts to establish the level of rent you can comfortably afford |  | 2020-09-04
19 | Contact ProVision preferred referral partners to discuss your plans and arrange quotes for your fitout if this is required | Refer to the 'More about your fitout' link and contact Business Services to discuss options | 2020-09-04
20 | Download the WOW fitout examples and tips for your practice for inspiration and understanding | Refer to the 'More about your fitout' link | 2020-09-04
72 | Develop shopfront, windows and internal signage | Engage & create a brief for graphic designer | 2020-09-04
74 | Set-up Google My Business listing | Dedicate a team member to manage | 2020-09-04
75 | Set-up Facebook account and update 2-3 times per week | Dedicate a team member for content production | 2020-09-04
17 | Familiarise yourself with some of the leasing principles in the document provided | Download the '5 tips to consider' document for leasing guidance | 2020-09-18
14 | Download the ‘Get Legally Set Up for Business’ checklist and ensure all items are actioned or scheduled for action | Refer to the 'Get legally set up for business' document | 2020-10-02
18 | Prior to signing lease, have Mark Corduff and your solicitor review it | Contact Business Services | 2020-10-02
48 | Why Choose You? Develop your "Why choose us" key points of difference | Clarify your 'brand' position & point of difference | 2020-10-02
49 | Identify yourTarget Market | Council Census Analysis & Surrounding Suburbs | 2020-10-02
50 | Clarify your patient 'Type' | High End, Middle Market, Value Patient | 2020-10-02
51 | Decide on your budget spend for inventory | How much has been put aside in your original business plan to purcahse frame stock and does this need to be revised? | 2020-10-02
52 | Look at & decide on display capacity (How many units will be on display & what additional stock you will hold on hand [1-2 units]) | What unit numbers do you need for an impactful visual display ? | 2020-10-02
53 | Decide on gender split & display capacity by gender & demographic | What is the percentage of stock mix by Womens, Mens (and kids if applicable)? This will come from your census report , a historical range review or the previous practice sell thru if available | 2020-10-02
76 | Develop your stationery - Business cards - Letterhead - Warranty cards - Glasses care cards | Engage & create a brief for graphic designer | 2020-10-02
77 | Develop marketing communication plan to patients including : relaunch postcards ,SMS and emails | Engage & create a brief for graphic designer | 2020-10-02
78 | Create google search ads, refer to ProVision for Google advertising instructions. | Create search ads required to promote practice | 2020-10-02
54 | Working with your BC , identify best suppliers for your target market | Reference: Preferred Supplier handbook & Top 50 Brands by Price point | 2020-10-16
31 | Create Position Descriptions for all positions | Can be found in recruitment framework | 2020-10-23
32 | Review Master Task List for the Practice to ensure all duties for your practice are included and also are allocated to team members |  | 2020-10-23
33 | Review the Recruitment Framework to gain a richer understanding of the recruiting process and how PV can support you |  | 2020-10-23
21 | Organise Utilities (Gas, Electricity, Internet) |  | 2020-10-30
23 | Purchase an accounting software system |  | 2020-10-30
24 | Access ProLearnMAX - Financial Foundations | Complete all modules to increase your financial knowledge | 2020-10-30 |  | https://prolearnmax.provision.com.au/admin/login-next.php
34 | Contact People and Culture Team to commence recruiting process |  | 2020-10-30
55 | Organise time to meet with frame suppliers | Ensure to be clear on units by display, gender split, OTB & under stock to be held (1-2 units) when meeting with reps | 2020-10-30
56 | Negotiate terms with supplier prior to signing off purchase | Is this consignment? Are there extended terms? What is the agreed rotation policy and the exit strategy by brand? Do you have an opening order /new memebr offers ? | 2020-10-30
57 | Clarify delivery dates for frame orders prior to practice opening | What is the turnaround time from order to deliver and will this be in time for set up & launch? | 2020-10-30
79 | Arrange Practice photography | Engage local photographer | 2020-10-30
80 | Create Launch Event. Invite staff that work in local area, local health professionals and VIPS from your local area and your database | Engage a supplier & create a brief for graphic designer | 2020-10-30
81 | Create interchangeable practice A-Frame with rotational messages |  | 2020-10-30
84 | Research local sponsorship opportunities |  | 2020-10-30
85 | Local newspaper advertising and editorials if relevant | sourcing quote from local provider | 2020-10-30
86 | Local Radio advertising if relevant | sourcing quote from local provider | 2020-10-30
87 | Local TV advertising (regional) if relevant | sourcing quote from local provider | 2020-10-30
88 | Update practice pages on the ProVision consumer website on a monthly basis | Dedicate a team member to manage | 2020-10-30
89 | Create a Facebook Advertising plan (refer to ProVision's member site to learn about Facebook Advertising) | Dedicate a team member for content production | 2020-10-30
94 | Obtain your Log in details from Australian Retialers Association (ARA) | Call ARA on 1300 368 041 Take option 1 (one).Quote your PV Member number and they will give new login details. Alternatively contact Kylie Parry, People and Culture Advisor on (03) 8544 3906 or email: kparry@provision.com.au | 2020-10-30
95 | Login to ARA site and familiarise yourself with Employee Agreement templates , policy documents and the Award conditions |  | 2020-10-30 |  | https://www.enablehr.com.au/ara/
96 | Access ARA Instructions on "How To Create a policy | insert link to ARA "How to Create a Policy Document" (new Document) | 2020-10-30
97 | Produce all policies relevant to your practice through ARA portal | Select each policy relevant to your practice , complete details required in the templates. Make one copy availble to the team to read and file on copy in your policy and procedure file for future reference | 2020-10-30
98 | Review AWARD conditions and salary ranges for each position on ARA website |  | 2020-10-30
58 | Implement pricing strategy | Work with you BC to create a pricing strategy that delivers strong margin and clear price points. | 2020-11-13
29 | Review and refine your financial forecasts and assumptions | Review all data on P&L and Cash Flow statement to ensure accuracy and achievable - Refer your Business Coach for guidance | 2020-11-20
30 | Enter data into accounting software to create full year budget P&L | Your Accountant or Bookkeeper will be able to complete this task | 2020-11-20
22 | Rent payments & bond (or bank guarantee) to be organised with landlord | Contact your landlord | 2020-11-27
35 | Ensure all contracts for team members are finalised | This time frame will vary depending on the notice period of the applicant | 2020-11-27
47 | Start your professional development as a business owner by making an appointment with your Business Coach to create your development plan | The plan might include reading The Carrot Principle, Dare to Lead and Fixing Communication | 2020-11-27
59 | Arrange brand training on frames and technical training for lenses | Dependent on recruitment stage it will be of benefit to have a training night with a couple of lead suppliers on the features and benefits of the brands and lenses sold in practice | 2020-11-27
60 | Delivery & indentation of frame stock into system | This date should have been agreed during closing negotiations with frame suppliers | 2020-11-27
61 | Inline with delivery, enter SOH into the system | Ensure to clasify as specifically as possible (style, pp, gender, SKU) as this will make reporting easier later on when analysing sell-thru. Confirm correct delivery and raise any discrepancies with supplier now | 2020-11-27
66 | Decide which price tags you will use | Source price tag/ barcoding system | 2020-11-27
67 | Check with Practice Management System (PMS )provider which barcode scanner is compatable with your PMS soft ware >> Purchase barcode scanner | This will increase accurancy and speed for all stock entry , POS transactions and stocktakes | 2020-11-27
82 | Develop relationships with GPs and specialists in local area. Develop - letter of introduction and introduce your new owner | Refer Us materials in GP section of optom.provision.com.au | 2020-11-27
83 | Develop cross promotional offers with local businesses where appropriate |  | 2020-11-27
90 | Invest in eye-catching window displays (consider window dresser) |  | 2020-11-27
92 | Liase with My Health First to ensure their software is embedded into your website |  | 2020-11-27
93 | Complete application for My Health First ( online booking) |  | 2020-11-27
99 | Create Employee Agreements ( Contracts) through enable HR (ARA) |  | 2020-11-27
100 | Enter each team members details onto your EnableHR portal for easy management of empolyee details,perfomance management etc |  | 2020-11-27
62 | Finalise Visual Merchandising Plan-O-Gram | Work with BC | 2020-12-04
36 | All new team members to complete Induction module on ProLearn Max plus complete and bespoke additional in practice induction |  | 2020-12-11
63 | ProSupply and Supply & Fit training | Team & owner training with BC or online training modules | 2020-12-11
43 | Set Team Meeting dates for 12 months and publish to team |  | 2020-12-18
44 | Diarise Performance Management Discussions for each team member |  | 2020-12-18
45 | Block off weekly time to observe each team members behaviour and performance | Allowing time every week for this will be one of you greatest investments in the positive culture and performance of your team | 2020-12-18
46 | Create a Team Recognition Plan |  | 2020-12-18
64 | Plan to complete a physical stocktake on or around settlement day |  | 2020-12-18
65 | Develop a simple lens pricing matrix document to assist the team to explain to customers the features ana benefits of the lenses in each price category | Ask your Business Coach for examples | 2020-12-18
68 | Arrange PMS system training for the Team |  | 2020-12-18
70 | Merchandise frames into display | Work to Plan-o-Gram | 2020-12-18
91 | Register for any relevant ProVision marketing campaigns. | Register for the campaign | 2020-12-18
69 | If transferring from paper patient record cards to digital patient records decide the process . | Refer to your Business Coach for suggestions | 2020-12-25
37 | Diarise new employee formal feedback sessions for end of week 1 | End of week 1 | 2021-01-01
38 | Diarise new employee feedback sessions for end of week 2 | End of week 2 | 2021-01-08
39 | Diarise new employee formal feedback sessions foe end of month 1 | End of month 1 | 2021-01-22
40 | Diarise new employee formal feedback sessions for end of month 2 | End of month 2 | 2021-02-19
41 | Diarise new employee formal feedback sessions for end of month 3 | End of month 3 | 2021-03-26
42 | Diarise new employee formal feedback sessions pror to the completeion of probation period | Prior to completion of probation period | 2021-03-26
101
102
Formulas:
Target Start date for task = IFNA(IF(VLOOKUP([Column1],'New Launch Menu'!$A3:K111,7,FALSE)=0,"",(VLOOKUP([Column1],'New Launch Menu'!$A3:K111,7,FALSE))),"")

## Specific Options Menu (hidden)
Marketing
Offer
Money
Dream Team
Consistent and Legal
Location
Bus plan to Reality

## Marketing (hidden)
Launch Pro Check List for Opening
The checklist assumes the owner has already located a Practice that they is in the process of purchasing
| Task | Comments | Approx. cost if known | LEAD TIME FROM OPENING DATE in WEEKS | OPENING DATE | Target Start date for task | Owner of Task | Progress Comments | Complete
1 | Decide on - Develop New Logo | Engage & create a brief for graphic designer | 500 | 20 | 2020-12-25 | 2020-08-07
2 | Develop shopfront, windows and internal signage | Engage & create a brief for graphic designer | 2000 | 20 | 2020-12-26 | 2020-08-08
3 | Create an independent practice website that compliments your new practice fit out |  |  | 20 | 2020-12-27 | 2020-08-09
4 | Set-up and update Google+ and Google My Business listing | Dedicate a team member to manage |  | 20 | 2020-12-28 | 2020-08-10
5 | Set-up Facebook account and update 2-3 times per week | Dedicate a team member for content production | 200 | 20 | 2020-12-29 | 2020-08-11
6 | Stationery - Business cards - Letterhead - Warranty cards - Glasses care cards | Engage & create a brief for graphic designer | 500 | 16 | 2020-12-30 | 2020-09-09
7 | Develop marketing Communication plan to patients including : relaunch postcards ,SMS and emails | Engage & create a brief for graphic designer | 2 | 12 | 2020-12-31 | 2020-10-08
8 | Create Digital google search ads, refer to ProVision for Google advertising instructions. | Create search ads required to promote practice | 300 | 12 | 2021-01-01 | 2020-10-09
9 | Practice Photography | Engage local photographer | 1600 | 8 | 2021-01-02 | 2020-11-07
10 | Create launch event. Invite staff that work in local area, local health professionals and VIPS from your local area and your database | Engage a supplier & create a brief for graphic designer |  | 8 | 2021-01-03 | 2020-11-08
11 | Interchangeable practice A-Frame with rotational messages |  | 350 | 8 | 2021-01-04 | 2020-11-09
12 | Develop relationships with GPs and specialists in local area. Develop - letter of introduction and introduce your new owner | Refer Us materials in GP section of optom.provision.com.au |  | 8 | 2021-01-05 | 2020-11-10
13 | Develop cross promotional offers with local businesses where appropriate |  |  | 8 | 2021-01-06 | 2020-11-11
14 | Local Sponsorship |  |  | 8 | 2021-01-07 | 2020-11-12
15 | Local newspaper advertising and editorials | sourcing quote from local provider |  | 8 | 2021-01-08 | 2020-11-13
16 | Local Radio advertising | sourcing quote from local provider |  | 8 | 2021-01-09 | 2020-11-14
17 | Local TV advertising (regional) | sourcing quote from local provider |  | 8 | 2021-01-10 | 2020-11-15
18 | Update practice pages on the ProVision consumer website on a monthly basis | Dedicate a team member to manage |  | 8 | 2021-01-11 | 2020-11-16
19 | Facebook Advertising (refer to ProVision's member site to learn about Facebook Advertising) | Dedicate a team member for content production | 200 | 8 | 2021-01-12 | 2020-11-17
20 | Invest in eye-catching window displays (consider window dresser) |  | 250 | 4 | 2021-01-13 | 2020-12-16
21 | Register for any relevant ProVisionMarketing campaign. | Register for the campaign |  | 1 | 2021-01-14 | 2021-01-07
22 | Ensure you have an online booking function built into your website |  | ? | 8 | 2021-01-15 | 2020-11-20
Formulas:
Target Start date for task = IFERROR(IF([OPENING DATE]-7*[LEAD TIME FROM OPENING DATE in WEEKS]<=0,"",[OPENING DATE]-7*[LEAD TIME FROM OPENING DATE in WEEKS]),"")

## Offer (hidden)
Launch Pro Check List for opening
The checklist assumes the owner has already located a Practice that he is in the process of purchasing
| Task | Comments | Approx. cost if known | LEAD TIME FROM OPENING DATE in WEEKS | Completion Target Date | Target Start date for task | Owner of Task | Progress Comments | Complete
23 | Why Choose You' | Clarify your 'brand' position & POD |  | 12 | 2020-12-25 | 2020-10-02
24 | Identify Target Market | Council Census Analysis & Surrounding Suburbs |  | 12 | 2020-12-26 | 2020-10-03
25 | Clarify 'Type' of Patient | High End, Middle Market, Value Patient |  | 12 | 2020-12-27 | 2020-10-04
26 | Decide on Budget Spend | How much has been put aside in your original business plan to purcahse frame stock and does this need to be revised? |  | 12 | 2020-12-28 | 2020-10-05
27 | Look at & decide on Display Capacity (how many units will be on display & what will you hold on hand [1-2 units]) | What unit numbers do you need for an impactful visual display |  | 12 | 2020-12-29 | 2020-10-06
28 | Decide on Gender Split & Display Capacity by Gender & Demographic | What is the percentage mix by Womens, Mens (and kids if applicable): This will come from your census report or an historical range review of the previous practice sell thru if available |  | 12 | 2020-12-30 | 2020-10-07
29 | Working with your BC identify best suppliers for your target market | Reference: Preferred Supplier handbook & Top 50 Brands by Price point |  | 10 | 2020-12-31 | 2020-10-22
30 | Organize time to meet w/ Frame Suppliers | Ensure to be clear on units by display, gender split, OTB & under stock to be held (1-2 units) when meeting with reps |  | 8 | 2021-01-01 | 2020-11-06
31 | Negotiate Terms Prior to Signing Off Purchase | Is this consignment? Are there extended terms, rotation, exit strategy by brand? |  | 8 | 2021-01-02 | 2020-11-07
32 | Clarify Delivery Dates Prior to Opening | What is the turnaround time from order to deliver and will this be in time for set up & launch? |  | 8 | 2021-01-03 | 2020-11-08
33 | Implement Pricing Strategy | Work with you BC to create a pricing strategy that delivers strong margin and clear price points. |  | 6 | 2021-01-04 | 2020-11-23
34 | Brand Training on Frames | Dependent on recruitment stage it will be of benefit to have a training night with a couple of lead suppliers on the features and benefits of the brands that will be sold in practice |  | 4 | 2021-01-05 | 2020-12-08
35 | Delivery & indentation of frame stock into system | This date should have been agreed during closing negotiations |  | 4 | 2021-01-06 | 2020-12-09
36 | Inline w/ delivery Indent SOH into the system | Ensure to clasify as specifically as possible (style, pp, gender, SKU) as this will make reporting easier later on when analysing sell-thru. Confirm correct delivery and raise any discrepancies with supplier now |  | 4 | 2021-01-07 | 2020-12-10
37 | Create Visual Merchandising Plan-O-Gram | Work with BC |  | 3 | 2021-01-08 | 2020-12-18
38 | ProSupply & Supply & Fit Training | Team & Owner training w/ BC |  | 2 | 2021-01-09 | 2020-12-26
39 | Merchandise Frames into display | Work to Plan-o-Gram |  | 1 | 2021-01-10 | 2021-01-03
Formulas:
Target Start date for task = IFERROR(IF([Completion Target Date]-7*[LEAD TIME FROM OPENING DATE in WEEKS]<=0,"",[Completion Target Date]-7*[LEAD TIME FROM OPENING DATE in WEEKS]),"")

## Money (hidden)
Launch Pro Check List for opening
The checklist assumes the owner has already located a Practice that he is in the process of purchasing
| Task | Comments | Approx. cost if known | LEAD TIME FROM OPENING DATE in WEEKS | Completion Target Date | Target Start date for task | Owner of Task | Progress Comments | Complete
40 | Purchase an Accouting Software System |  |  | 12 | 2020-12-25 | 2020-10-02
41 | Acess ProLearnMax - Financial Foundations | Completed all modules to increase your financial knowledge |  | 11 | 2020-12-27 | 2020-10-11
42 | Set your financial goals | Where is the business now? Where is the business heading How is the business going to get there? Set long term strategic goals |  | 10 | 2020-12-30 | 2020-10-21
43 | Calculate your costs | Make a list of expenses - Refer your Business Coach Eg Wages, Rent, Utilities, Fees, Marketing, Accouting etc |  | 10 | 2021-01-04 | 2020-10-26
44 | Predict your sales income | Consultation Income Retail Income Sundry Income |  | 10 | 2021-01-07 | 2020-10-29
45 | Complete the P&L/Cashflow Template | insert link Refer Business Coach for guidance |  | 10 | 2021-01-11 | 2020-11-02
46 | Review and Refine | Review all data on P&L and Cash Flow statement to ensure accuracy and achievable - Refer your Business Coach for guidance |  | 10 | 2021-01-14 | 2020-11-05
47 | Enter data into Accounting software to create full year budget P&L |  |  | 9 | 2021-01-15
Formulas:
Target Start date for task = IFERROR(IF([Completion Target Date]-7*[LEAD TIME FROM OPENING DATE in WEEKS]<=0,"",[Completion Target Date]-7*[LEAD TIME FROM OPENING DATE in WEEKS]),"")

## Dream Team (hidden)
Launch Pro Check List for opening
The checklist assumes the owner has already located a Practice that he is in the process of purchasing
| Task | Comments | Approx. cost if known | LEAD TIME FROM OPENING DATE in WEEKS | Completion Target Date | Target Start date for task | Owner of Task | Progress Comments | Complete
47 | Create Position Descriptions for all positions | Can be found in recruitment framework |  | 9 | 2020-12-26 | 2020-10-24
48 | Review Master Task List for the Practice to ensure all duties for your practice are included and also are allocated to team members |  |  |  | 2020-12-26 | 2020-12-26
49 | Review the Recruitment framework to gain a richer understanding of the recruiting process and how PV can support you |  |  | 9 | 2020-12-26 | 2020-10-24
50 | Contact People and Culture Team to commence recruiting process |  |  | 8 | 2020-12-26 | 2020-10-31
51 | Ensure all contracts for team members are finalised | This time frame will vary depending on the notice period of the applicant |  | 4 | 2020-12-26 | 2020-11-28
52 | All New Team members to complete Induction module on ProLearn Max plus complete and bespoke additional in practice induction |  |  | 0 | 2020-12-26 | 2020-12-26
53 | Diarise new employee formal feedback sessions | End of week 1 |  | -1 | 2020-12-26 | 2021-01-02
54 | Diarise new employee feedback sessions | End of week 2 |  | -2 | 2020-12-26 | 2021-01-09
55 | Diarise new employee formal feedback sessions | End of month 1 |  | -4 | 2020-12-26 | 2021-01-23
56 | Diarise new employee formal feedback sessions | end of month 2 |  | -8 | 2020-12-26 | 2021-02-20
57 | Diarise new employee formal feedback sessions | End of month 3 |  | -13 | 2020-12-26 | 2021-03-27
58 | Diarise new employee formal feedback sessions | Prior to completion of probation period |  | -13 | 2020-12-26 | 2021-03-27
59 | Set Staff meeting dates for 12 months and publish to team |  |  | 1 | 2020-12-26 | 2020-12-19
Formulas:
Target Start date for task = IFERROR(IF([Completion Target Date]-7*[LEAD TIME FROM OPENING DATE in WEEKS]<=0,"",[Completion Target Date]-7*[LEAD TIME FROM OPENING DATE in WEEKS]),"")

## Consistent and Legal (hidden)
Launch Pro Check List for opening
The checklist assumes the owner has already located a Practice that he is in the process of purchasing
| Task | Comments | Approx. cost if known | LEAD TIME FROM OPENING DATE in WEEKS | Completion Target Date | Target Start date for task | Owner of Task | Progress Comments | Complete
60 | Obtain your Log in details from Australian Retialers Association (ARA) | Call ARA on 1300 368 041 Take option 1 (one).Quote your PV Member number and they will give new login details. Alternatively contact Kylie Parry, People and Culture Advisor on (03) 8544 3906 or email: kparry@provision.com.au |  | 12 | 2020-12-25 | 2020-10-02
61 | Login to ARA site | https://www.enablehr.com.au/ara/ |  |  | 2020-12-30
62 | Access ARA Instructions on "How To Create a policy | insert link to ARA "How to Create a Policy Document" (new Document) |  | 12 | 2021-01-01 | 2020-10-09
63 | Produce all policies relevant to your practice | select each poliy elevant to your practice and fill in the details required in the templates |  | 12 | 2021-01-03 | 2020-10-11
64 | Review and refine | Review each policy created |  | 4 | 2021-01-05 | 2020-12-08
65 | Print each policy | Print 2 copies of each policyMake one copy aviable to the team to read and file on copy in your policy and procedure file for future reference |  | 4 | 2021-01-07 | 2020-12-10
Formulas:
Target Start date for task = IFERROR(IF([Completion Target Date]-7*[LEAD TIME FROM OPENING DATE in WEEKS]<=0,"",[Completion Target Date]-7*[LEAD TIME FROM OPENING DATE in WEEKS]),"")

## Location (hidden)
Launch Pro Check List for opening
The checklist assumes the owner has already located a Practice that he is in the process of purchasing
| Task | Comments | Approx. cost if known | LEAD TIME FROM OPENING DATE in WEEKS | Completion Target Date | Target Start date for task | Owner of Task | Progress Comments | Complete
67 | Discuss and lease and fit out questions with Business Services at ProVision | Reach out to Mark Corduff |  | 24 | 2020-12-26 | 2020-07-11
68 | Complete your sales and expense forecast to establish the level of rent you can comfortably afford |  |  | 24 | 2020-12-27 | 2020-07-12
69 | Familiarise yourself with some of the leasing principles in the document provided |  |  | 20 | 2020-12-28 | 2020-08-10
70 | Prior to siging lease, have Mark Corduff and your solicitor review it |  |  | 20 | 2020-12-29 | 2020-08-11
71 | Contact our preferred referral partners to discuss your plans and arrange quotes for your fitout |  |  | 24 | 2020-12-30 | 2020-07-15
72 | Download the fitout examples and tips for your practice for inspiration and understanding |  |  | 24 | 2020-12-31 | 2020-07-16
73 | Organise Utilities (Gas, Electricity, Internet) |  |  | 12 | 2021-01-01 | 2020-10-09
74 | Rent payments & bond (or bank guarantee) to be organised with landlord |  |  | 4 | 2021-01-02 | 2020-12-05
Formulas:
Target Start date for task = IFERROR(IF([Completion Target Date]-7*[LEAD TIME FROM OPENING DATE in WEEKS]<=0,"",[Completion Target Date]-7*[LEAD TIME FROM OPENING DATE in WEEKS]),"")

## Bus plan to Reality (hidden)
Launch Pro Check List for opening
The checklist assumes the owner has already located a Practice that he is in the process of purchasing
| Task | Comments | Approx. cost if known | LEAD TIME FROM OPENING DATE in WEEKS | Completion Target Date | Target Start date for task | Owner of Task | Progress Comments | Complete
75 | Create your business plan | Reach out to your Business Coach for template and guidance |  | 24 | 2020-12-26 | 2020-07-11
75 | Secure an Accountant |  |  | 20 | 2020-12-27 | 2020-08-09
75 | Secure a Solicitor |  |  | 20 | 2020-12-28 | 2020-08-10
75 | Secure a Financial Advisor |  |  | 20 | 2020-12-29 | 2020-08-11
75 | Decide on your company structure | Refer to ‘Tips on Establishing Your Structure’ |  | 20 | 2020-12-30 | 2020-08-12
75 | Register Company name |  |  | 18 | 2020-12-31 | 2020-08-27
75 | Register ABN, TFN and GST |  |  | 18 | 2021-01-01 | 2020-08-28
75 | Secure Insurances: • Professional Indemnity insurance • Public Liability | OAA Ph: (03) 96636833 Membership of Optometrists Association Australia includes Professional Indemnity Insurance. |  | 18 | 2021-01-02 | 2020-08-29
75 | Other insurances as required: • Building/stock • Income protection • Loan protection • Life | Membership of Optometrists Association Australia includes Professional Indemnity Insurance. |  | 18 | 2021-01-03 | 2020-08-30
75 | Schedule and diarise fortnightly catch ups with Business Coach (for ProVision Comprehensive Members) |  |  | 18 | 2021-01-04 | 2020-08-31
75 | Register for ProVision leasing assistance |  |  | 24 | 2021-01-05 | 2020-07-21
75 | Secure Bank & set up Business Bank account |  |  | 18 | 2021-01-06 | 2020-09-02
75 | Organise finance if required | Refer to the ‘Discover Finance Options For You’ document |  | 20 | 2021-01-07 | 2020-08-20
75 | Download the ‘Get Legally Set Up for Business’ checklist and ensure all items are actioned or scheduled for action |  |  | 12 | 2021-01-08 | 2020-10-16
Formulas:
Target Start date for task = IFERROR(IF([Completion Target Date]-7*[LEAD TIME FROM OPENING DATE in WEEKS]<=0,"",[Completion Target Date]-7*[LEAD TIME FROM OPENING DATE in WEEKS]),"")

## Sheet3 (hidden)
Marketing
Offer
Money
Dream Team
Consistent and Legal
Location
Bus plan to Reality